| ### Typical Production Schedule |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week | SUN * | MON | TUE | WED | THU | FRI | SAT |
| Pre-Production schedule: Director identifies and works with AD and designers; meets with OLT support |  |  |  |  |  |  |  |
|  | draft set/costume Designs | 1st Production meeting with OLT support** | Prep for Auditions | ID crews reqs, begin recruiting | ID rehearsal props list, sent pieces |  | Auditions 1PM-5PM |
|  |  | Audition/ call-backs |  |  |  |  |  |
|  |  | set ground plan due to TD |  |  |  |  |  |
|  |  |  |  |  | 1ST READ *** RH 7-11 pm |  |  |
|  | RH 1-5 or 7-11 pm |  | RH 7-11 pm |  | RH 7-11 pm |  |  |
|  | RH 1-5 or 7-11 pm |  | RH 7-11 pm |  | RH 7-11 pm |  |  |
|  | RH 1-5 or 7-11 pm |  | RH 7-11 pm |  | RH 7-11 pm |  |  |
|  | RH 1-5 or 7-11 pm |  | RH 7-11 pm |  | RH 7-11 pm |  |  |
|  | RH 1-5 or 7-11 pm | Approved set designs to TD |  | RH 7-11 pm |  | RH 7-11 pm |  |
|  | RH 1-5 or 7-11 pm | RH 7-11 pm |  | RH 7-11 pm |  | RH 7-11 pm |  |
|  | RH 1-5 or 7-11 pm | RH 7-11 pm |  | RH 7-11 pm |  | RH 7-11 pm |  |
|  | RH 1-5 or 7-11 pm | RH 7-11 pm |  | RH 7-11 pm |  | RH 7-11 pm |  |
|  | RH 1-5 or 7-11 pm | RH 7-11 pm 2nd Production Meeting**- | sound/ light teams mtg | RH 7-11 pm Program Deadline | (video clips) Deadline | RH 7-11 pm |  |
|  | RH 1-5 pm or 7-11 LX hang OLT TECH nite | RH 7-11 pm set in place - lx focus | ? STAGE 7-11 pm SX/LX levels | STAGE 7-11 pm | STAGE 7-11 pm | STAGE 7-11 pm run for LX | Stage? |
|  | STAGE 1-11 pm | STAGE 7-11 pm | STAGE 7-11pm | TECH REH Photo Call? | TECH REH Photo Call? | DRESS/ Preview? | Stage? |
|  | Preview? | Stage? | Stage? | Opening Night | RUN | RUN | RUN |
|  | Mat 2:30pm | No Show | No Show | RUN | RUN | RUN | RUN |
|  | Mat 2:30pm | No Show | No Show | RUN | RUN | RUN Crew Party | RUN - CLOSE & Strike |
|  |  |  | POST- Prod MTG - clean costumes | costumes to storage |  |  |  |

*  Sundays  - next play “up” decides Sunday afternoon or evening rehearsals

** OLT  Support: Tech Director, Stage Carpenter/Technician, Production Support, Artistic Director, Volunteer Liaison, President, etc

January 2026